## Sheet1
Meeting Logs
Group Members: | William Read | Euan Campbell | Ty Osiefa
| Dean Ivanov | Liam Walsh
| Date | Tasks Set | Tasks Completed | Comments
Week 1 | 2017-01-23 | - Understanding the brief - Breaking down the task into functionalities - Allocation of functionalities |  | - Each group member has different skill levels, posing risks for later when we come to project creation
2017-01-25
Week 2 | 2017-01-30 | - Breakdown of tasks within own functionality - Paper-based prototype - Database design | - Breaking down the task into functionalities ✓ - Allocation of functionalities ✓ - Breakdown of tasks within own functionality ✓
2017-02-01
Week 3 | 2017-02-06 | - Use case diagram - Use case documentation - Class diagram - Flowchart - Database creation | - Paper-based prototype ✓ - Database design ✓
2017-02-08
Week 4 | 2017-02-13 | - Determine final protoype design - Completion of database creation | - Use case diagram ✓ - Use case documentation ✓ - Class diagram ✓ - Flowchart ✓
2017-02-15
Week 5 | 2017-02-20 | - Development of functionality - Catch up | - Database creation ✓ - Catch up ✓
2017-02-22
Week 6 | 2017-02-27 | - Demonstrate prototype 1 as split functionality | - Demonstrate prototype 1 as split functionality ✓
2017-03-01
Week 7 | 2017-03-06 | - Finish any imperfections in protoype 1 as per feedback | - Finish any imperfections in protoype 1 as per feedback ✓ | - Realisation that final project will only be the collaboration of a few functionalities due to some group members lacking in contribution
2017-03-08
Week 8 | 2017-03-13 | - Start working on prototype 2 and the collaboration of projects into a single entity | - Start working on prototype 2 ✓
2017-03-15
Week 9 | 2017-03-20 | - Adjust any previous diagrams based on changes made during the project - Development of prototype 2 | - Diagrams adjusted ✓
2017-03-22
Week 10 | 2017-03-27 | - Presentation of prototype 2 - Write-up of methods used during the project | - Presentation of prototype 2 ✓ - Write-up of methods used during the project ✓
2017-03-29
Week 11 | 2017-04-03 | - Completion of project through finishing any niche areas - Project Hand-in | - Completion of project through finishing any niche areas ✓ - Project Hand-in ✓
2017-04-05