## Sheet 1
Weekly Objectives | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Understanding the brief | bar: Week 1
Breaking down the task into functionalities | bar: Week 1
Allocation of functionalities | bar: Week 1
Breakdown of tasks within own functionality | bar: Week 2 to Week 3
Paper-based prototype | bar: Week 2 to Week 3
Database design | bar: Week 2 to Week 3
Use case diagram creation | bar: Week 3
Use case documentation creation | bar: Week 3
Class diagram creation | bar: Week 3 to Week 4
Flowchart creation | bar: Week 3 to Week 4
Database creation | bar: Week 3 to Week 4
Determine final protoype design | bar: Week 4 to Week 5
Development of functionality | bar: Week 5 to Week 7
Demonstrate prototype 1 as split functionality | bar: Week 6 to Week 7
Finish any imperfections in protoype 1 as per feedback | bar: Week 7
Start working on prototype 2 and the collaboration of projects into a single entity | bar: Week 8
Adjust any previous diagrams based on changes made during the project | bar: Week 9 to Week 10
Development of prototype 2 | bar: Week 10
Presentation of prototype 2 | bar: Week 10
Write-up of methods used during the project | bar: Week 10
Completion of project through finishing any niche areas | bar: Week 11
Project Hand-in | bar: Week 11